## Sheet1
# | Action Item | Category | Committee | PFC Staff Lead | 2017 Date | 2018 Date | Status
1 | Form Leadership work team | Project Management | Soirée Leadership Team | Linda Blanton | 2016-09-14 | 2017-09-14 | Completed
2 | Establish event budget | Project Management | Soirée Leadership Team | Linda Blanton | 2016-10-18 | 2017-10-18 | Completed
3 | Establish event goals and objectives | Project Management | Soirée Leadership Team | Linda Blanton | 2016-10-18 | 2017-10-18 | Completed
4 | Identify venue and negotiate details | Project Management | Soirée Leadership Team | Linda Blanton | 2016-10-18 | 2017-10-18 | Completed
5 | Select date | Project Management | Soirée Leadership Team | Linda Blanton | 2016-10-18 | 2017-10-18 | Completed
6 | Request to PNC Bank for Sponsorship | Sponsorship | Soirée Revenue Work Group | Mary Sonnenberg | 2016-12-22 | 2017-12-22 | Completed
7 | Identify sponsors/partners and create groups in salesforce | Sponsorship | Soirée Revenue Work Group | Linda Blanton | 2017-01-02 | 2018-01-02 | Completed
8 | Develop and produce Save the Date Card | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-01-06 | 2017-01-06 | Completed
9 | Develop and produce Sponsorship Brochure | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-01-06 | 2018-01-06 | Completed
10 | Recruit volunteers for the day before auction night activities. | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-09 | 2018-01-09 | Completed
11 | Create a Facebook event page | Publicity | Soirée Engagement Work Group | John Freudenberg | 2017-01-09 | 2017-01-09 | Completed
12 | Create event page on our website | Publicity | Soirée Engagement Work Group | John Freudenberg | 2017-01-09 | 2018-01-09 | Completed
13 | Create/maintain volunteer campaigns/jobs/shifts for Event Night | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-09 | 2017-01-09 | Completed
14 | Create/maintain volunteer campaigns/jobs/shifts for Set Up | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-09 | 2018-01-09 | Completed
15 | Identify job skills for each volunteer job in Salesforce | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-09 | 2018-01-09 | Completed
16 | Identify the Mission Moment Appeal | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-01-09 | 2017-01-09 | Completed
17 | Send out a digital “Save the Date” | Publicity | Soirée Engagement Work Group | John Freudenberg | 2017-01-09 | 2018-01-09 | Completed
18 | Send procurement letters and emails to collect items for auction packages | Auction | Soirée Revenue Work Group | John Freudenberg | 2017-01-09 | 2018-01-09 | Completed
19 | Send procurement letters and emails to collect items for chef circle - Ideally, it would be about 1 vendor per 50 people | Chef Circle | Soirée Revenue Work Group | John Freudenberg | 2017-01-09 | 2017-01-09 | Completed
20 | Send procurement letters and emails to collect items for dessert dash | Dessert Dash | Soirée Revenue Work Group | John Freudenberg | 2017-01-09 | 2018-01-09 | Completed
21 | Send procurement letters and emails to collect items for sponsors | Auction | Soirée Revenue Work Group | John Freudenberg | 2017-01-09 | 2018-01-09 | Completed
22 | Finalize contract for professional sound and lighting company | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-01-10 | 2018-01-10 | Completed
23 | Finalize contract for venue to Anna | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-01-10 | 1/10/201 | Completed
24 | Order raffle tickets, beads and drink tickets | Event Production | Soirée Logistic Work Group | Daniele Malvesti | 2017-01-10 | 2018-01-10 | Completed
25 | Set up Auction Consignment suitcase with Winspire & | Auction | Soirée Revenue Work Group | Linda Blanton | 2017-01-10 | 2018-01-10 | Completed
26 | Host a Soirée “Call-A-Thon” party at the Partnership | Sponsorship | Soirée Revenue Work Group | John Freudenberg | 2017-01-12 | 2018-01-12 | Completed
27 | Crown Ticket Office Agreement | Tickets | Soirée Revenue Work Group | Linda Blanton | 2017-01-13 | 2018-01-13 | Completed
28 | Develop a promo video and post on YouTube and our Facebook page (Perry) | Publicity | Soirée Engagement Work Group | John Freudenberg | 2017-01-13 | 2018-01-13 | Completed
29 | Finalize contract for fire performer | Entertainment | Soirée Logistic Work Group | Linda Blanton | 2017-01-13 | 2018-01-13 | Completed
30 | PNC Distribution Committee meeting mid-January | Sponsorship | Soirée Revenue Work Group | Mary Sonnenberg | 2017-01-15 | 2018-01-15 | Completed
31 | Reserve Auctionpay card readers or terminals for on-site credit card processing | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-01-17 | 2018-01-17 | Completed
32 | Create Chef Circle Contract | Event Production | Soirée Logistic Work Group | Anna Hall | 2017-01-18 | 2018-01-18 | Completed
33 | Recruit event committee, event manager or chair and establish sub-committee chairs | Project Management | Soirée Leadership Team |  | 2017-01-18 | 2017-10-18 | Completed
34 | Develop and produce Invitation & posters | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-01-24 | 2018-01-24 | Completed
35 | Invitation to Systel | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-01-24 | 2018-01-24 | Completed
36 | PNC Response | Sponsorship | Soirée Revenue Work Group | Mary Sonnenberg | 2017-01-24 | 2018-01-24 | Completed
37 | Pre-donations for Special Appeal | Mission Moment | Soirée Revenue Work Group | Linda Blanton | 2017-01-24 | 2018-01-24 | Completed
38 | Engage Board Members with Soiree | Volunteer Management | Soirée Engagement Work Group | Mary Sonnenberg | 2017-01-26 | 2017-12-15 | Completed
39 | Send follow up email to Board attendees on commitment | Publicity | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-27 | 2018-01-27 | Completed
40 | Order supplies for Checkout Work Stations | Gaming | Soirée Logistic Work Group | Nicloe Miller | 2017-01-30 | 2018-01-30 | Completed
41 | Recruit Décor Team members | Décor | Soirée Logistic Work Group | Rebecca Beck | 2017-01-30 | 2018-01-30 | Completed
42 | Select volunteers for Auction night | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-01-30 | 2018-01-30 | Completed
43 | Weekly Soirée Meeting | Project Management | Soirée Leadership Team | Mary Sonnenberg | 2017-01-30 | 2018-01-30 | Completed
44 | Weekly Soirée Meeting Update | Project Management | Soirée Leadership Team | Daniele Malvesti | 2017-01-31 | 2018-01-31 | Completed
45 | Get invitation to Systel | Publicity | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-01 | 2018-02-01 | Completed
46 | Public On Sale of Soiree Tickets | Tickets | Soirée Revenue Work Group | Linda Blanton | 2017-02-01 | 2018-02-01 | Completed
47 | Inivite list reconciled with Saleforce and other excel spreadsheet | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-02 | 2018-02-02 | Completed
48 | Bulk Mail US Postal Service Gateway https://gateway.usps.com/eAdmin/view/signin | Publicity | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-03 | 2018-01-20 | Completed
49 | Create plan for social media buzz by creating a hashtag for your event. | Publicity | Soirée Engagement Work Group | Rebecca Beck | 2017-02-03 | 2018-02-03 | Completed
50 | PTR for aerialist to Anna | Entertainment | Soirée Logistic Work Group | Linda Blanton | 2017-02-03 | 2018-02-03 | Completed
51 | Set up Soiree Event Slideshow PowerPoint | Event Slideshow PowerPoint | Soirée Engagement Work Group | Linda Blanton | 2017-02-03 | 2018-02-03 | Completed
52 | Coordinate any computer, printer, and on-site technical support | Event Production | Soirée Logistic Work Group | Steve Riley | 2017-02-04 | 2018-02-04 | Completed
53 | Approval of names for silent auctions by Soiree Board Leadership | Event Production | Soirée Engagement Work Group | Linda Blanton | 2017-02-05 | 2018-02-05 | Completed
54 | 1st Décor Team Meeting | Décor | Soirée Logistic Work Group | Rebecca Beck | 2017-02-06 | 2018-02-06 | Completed
55 | Harccopy Invitation mail out to a targeted invitation | Publicity | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-06 | 2018-02-06 | Completed
56 | Set up InDesign | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-06 | 2018-02-06 | Completed
57 | Weekly Soirée Meeting | Project Management | Soirée Leadership Team | Mary Sonnenberg | 2017-02-06 | 2018-02-06 | Completed
58 | Meet with Jean to discuss program template | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-07 | 2018-02-07 | Completed
59 | Reconcile Sponsors in Greater Giving to InDesign Document Under "Our Generous Sponsors" | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-07 | 2018-02-17 | Completed
60 | Set up InDesign Program Booklet Template - Cover and Header and Footer (Use Soiree Logo) | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-07 | 2018-02-07 | Completed
61 | Weekly Soirée Meeting Update | Project Management | Soirée Leadership Team | Daniele Malvesti | 2017-02-07 | 2018-02-07 | Completed
62 | Perform a site walk-through with the venue’s event manager | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-02-13 | 2018-02-13 | Completed
63 | Set up Groups in Greater Giving for Tables | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-13 | 2018-02-13 | Completed
64 | Set Up Tables in Grearter Giving | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-13 | 2018-02-13 | Completed
65 | Weekly Soirée Meeting | Project Management | Soirée Leadership Team | Mary Sonnenberg | 2017-02-13 | 2018-02-13 | Completed
66 | Make 162 passports consisting of two beads, 2 drink tickets and 40 tickets | Gaming | Soirée Logistic Work Group | Leslie Crist | 2017-02-14 | 2018-02-14 | Completed
67 | Make120 streamers of 40 tickets | Gaming | Soirée Logistic Work Group | Leslie Crist | 2017-02-14 | 2018-02-14 | Completed
68 | Weekly Soirée Meeting Update | Project Management | Soirée Leadership Team | Daniele Malvesti | 2017-02-14 | 2018-02-14 | Completed
69 | Create 4 30-second radio ad for Beasley to run | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-15 | 2018-02-15 | Completed
70 | Sponsorship forms and auction packages are due | Auction | Soirée Revenue Work Group | Daniele Malvesti | 2017-02-15 | 2018-02-15 | Completed
71 | Check request for vendors | Entertainment | Soirée Logistic Work Group | Linda Blanton | 2017-02-16 | 2018-02-16 | Completed
72 | Finalize 2017 PFC/City View Ad Agreement | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-16 | 2017-11-01 | Completed
73 | Finalize 2017 PFC/Systel Print Agreement | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-16 | 2017-11-01 | Completed
74 | Finalize floor plan | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-02-16 | 2018-02-16 | Completed
75 | Register your event on a variety of online event calendars | Publicity | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-16 | 2019-01-02 | Completed
76 | Review setup of Greater Giving with Carol Parker | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-16 | 2018-02-16 | Completed
77 | Text blast through MailChimp | Publicity | Soirée Engagement Work Group | John Freudenberg | 2017-02-16 | 2018-02-16 | Completed
78 | Determine banner signs (3 x 10) | Event Signage | Soirée Logistic Work Group | Daniele Malvesti | 2017-02-17 | 2018-02-17 | Completed
79 | Finalize 2017 PFC/FO Ad Agreement | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-17 | 2017-11-01 | Completed
80 | Order decoration supplies | Décor | Soirée Logistic Work Group | Rebecca Beck | 2017-02-17 | 2018-02-17 | Completed
81 | Secure a photographer for the entire evening | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-17 | 2018-02-17 | Completed
82 | Send request to top four sponsor levels requestin high resolution logo and copy ready ad for program | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-17 | 2018-02-17 | Completed
83 | Weekly Soirée Meeting - | Project Management | Soirée Leadership Team | Mary Sonnenberg | 2017-02-20 | 2018-02-20 | Completed
84 | Confirmed card reader scheduled for shipment - Called GG talked with Michelle | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-21 | 2018-02-21 | Completed
85 | Draft mission moment text | Event Program/ Catalog | Soirée Logistic Work Group | Linda Blanton | 2017-02-21 | 2018-02-21 | Completed
86 | Email to Board for last call for sponsor and auction items | Event Program/ Catalog | Soirée Engagement Work Group | Linda Blanton | 2017-02-21 | 2018-02-21 | Completed
87 | Notification to Soiree Volunteers for Orientation | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-02-21 | 2018-02-21 | Completed
88 | 4 x 5 Soiree Weekender Ad | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-23 | 2018-02-23 | Completed
89 | Banner signs to Fast Signs | Event Signage | Soirée Logistic Work Group | Daniele Malvesti | 2017-02-23 | 2018-02-23 | Completed
90 | Finish procurement. Enter final items into software. | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-23 | 2018-02-23 | Completed
91 | FOT eblast to 32,000 circulation | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-23 | 2018-02-23 | Completed
92 | 4 x 5 Saturday Extra Ad | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
93 | Assign items to live and silent auction sections | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
94 | Deadline for sponsors to get ad into event program | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
95 | Finalize Event Timeline | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
96 | Finalize Silent and Live Auction Packages | Auction | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
97 | Reserve Consighment Auction Items | Auction | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
98 | Sequence the live auction items | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
99 | Submitt sponsor level to marketing consultant | Event Program/ Catalog | Soirée Logistic Work Group | Linda Blanton | 2017-02-24 | 2018-02-24 | Completed
100 | Initiate Exclusive savings - Save 25% on Select Tickets with offer code: CARE | Tickets | Soirée Revenue Work Group | Linda Blanton | 2017-02-27 | 2018-02-27 | Completed
101 | Weekly Soirée Meeting | Project Management | Soirée Leadership Team | Mary Sonnenberg | 2017-02-27 | 2018-02-27 | Completed
102 | "Talk Back with Danny Highsmith”…featuring local public service discussions on WKML (95.7 FM) and BobFm (96.5FM) Recording | Publicity | Soirée Engagement Work Group | Mary Sonnenberg | 2017-02-28 | 2018-02-28 | Completed
103 | Feature Soiree on Fayetteville 180 | Advertising | Soirée Engagement Work Group | Mary Sonnenberg | 2017-02-28 | 2018-02-28 | Completed
104 | Gilbert Baez and Taylor Morgan with host “Community Matters” all shows are recorded and play back | Publicity | Soirée Engagement Work Group | Mary Sonnenberg | 2017-02-28 | 2018-02-28 | Completed
105 | Weekly Soirée Meeting Update | Project Management | Soirée Leadership Team | Daniele Malvesti | 2017-02-28 | 2018-02-28 | Completed
106 | FOT eblast to 32,000 circulation | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-03-01 | 2018-03-01 | Completed
107 | Order Green Screen from Five Star Entertainment | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-03-01 | 2018-03-01 | Completed
108 | Order Photo Booth from Five Star Entertainment | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-03-01 | 2018-03-01 | Completed
109 | Order Step and Repeat from StickersBanner.com | Publicity | Soirée Engagement Work Group | Linda Blanton | 2017-03-01 | 2018-03-01 | Completed
110 | Program/Catalog Deadline to Systel Print Shop | Event Program/ Catalog | Soirée Engagement Work Group | Linda Blanton | 2017-03-01 | 2018-03-01 | Completed
111 | Organize all auction items and displays for delivery to venue | Event Production | Soirée Logistic Work Group | Eileen Cedzo | 2017-03-03 | 2018-03-03
112 | Send Soiree Event Slideshow PowerPoint to Michael Parker | Event Slideshow PowerPoint | Soirée Engagement Work Group | Linda Blanton | 2017-03-03 | 2018-03-03 | Completed
113 | Assign bidder numbers to guests. | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06
114 | Contact Tony Williams of the Crown to get Pyro Permit $250 | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06 | Scheduled
115 | Finalize arrangements for computer and printer setup. | Event Production | Soirée Logistic Work Group | Steve Riley | 2017-03-06 | 2018-03-06
116 | Finalize PPT presentation | Event Slideshow PowerPoint | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06 | Scheduled
117 | Finazlize Silent Auction Bid Sheets | Auction | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06 | Scheduled
118 | Make sure all auction packages have their package number assigned and attached. | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06 | Scheduled
119 | Pre-Event Greater Giving Data Audit | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06 | Scheduled
120 | Review MPBA Event Night Checklist | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-06 | 2018-03-06
121 | Send day-of-event volunteer schedule to volunteers | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-06 | 2018-03-06
122 | Sponsor & Dessert Dash Donor Placards | Event Signage | Soirée Logistic Work Group | Lydia Wiles | 2017-03-06 | 2018-03-06
123 | Receive delivery of Auctionpay Card Readers. | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-03-07 | 2018-03-07 | Scheduled
124 | Print Catalog Addendum | Event Program/ Catalog | Soirée Engagement Work Group | Linda Blanton | 2017-03-08 | 2018-03-08
125 | Send Soiree Event Slideshow PowerPoint to Crown Coliseum | Event Slideshow PowerPoint | Soirée Engagement Work Group | Linda Blanton | 2017-03-08 | 2018-03-08 | Scheduled
126 | Conduct First Volunteer Training Session | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-09 | 2018-03-09 | Scheduled
127 | Create an addendum to the catalog for last-minute items. | Event Program/ Catalog | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-09 | 2018-03-09
128 | Create walk-in registration packets. | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
129 | Enter last minute registrations three days prior to the auction | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
130 | Finalize bidder packets: include a catalog, bidder number, and table number. | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
131 | Package items for Silent and Live Auction | Auction | Soirée Logistic Work Group | Lydia Wiles | 2017-03-09 | 2018-03-09
132 | Prepare Announcer Sheets |  | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
133 | Prepare Auctioneer Cards or Info Sheets | Auction | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
134 | Prepare Registration Packets for Auction | Registration | Soirée Logistic Work Group | Leslie Crist | 2017-03-09 | 2018-03-09
135 | Print bid sheets from Event Software Online. | Registration | Soirée Logistic Work Group | Linda Blanton | 2017-03-09 | 2018-03-09
136 | Assemble event materials and supplies to deliver to the venue | Event Production | Soirée Logistic Work Group | Eileen Cedzo | 2017-03-10 | 2018-03-10 | In Progress
137 | Conduct Last Volunteer Training Session | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-10 | 2018-03-10
138 | Create an organization contact sheet* to hand out at check-out | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
139 | Deliver all items and event materials to venue. | Event Production | Soirée Logistic Work Group | Eileen Cedzo | 2017-03-10 | 2018-03-10
140 | Enter last minute guests | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
141 | Establish a way to collect attendee updates and contact info. | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
142 | Match up each silent auction package with bid sheet. | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
143 | Print final day-of-event schedule and distribute to event staff and volunteer | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-10 | 2018-03-10
144 | Print out package list for verification of packages | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
145 | Print out placard signage for each silent auction item | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
146 | Print registration lists and all reports pertinent to the event. | Event Production | Soirée Logistic Work Group | Linda Blanton | 2017-03-10 | 2018-03-10
147 | Test and verify lighting settings and sound levels. | Event Production | Soirée Logistic Work Group | Mark Pezzella | 2017-03-10 | 2018-03-10
148 | The day of the event, complete on-site set-up | Event Production | Soirée Logistic Work Group | Eileen Cedzo | 2017-03-10 | 2018-03-10
149 | CheckEvent Slideshow PowerPoint | Event Slideshow PowerPoint | Soirée Engagement Work Group | Linda Blanton | 2017-03-11 | 2018-03-11
150 | Sign Next Year Contract | Post Event Wrap Up | Soirée Logistic Work Group | Linda Blanton | 2017-03-17 | 2018-03-17
151 | Conduct Post Auction Meeting to Critique Event with Auctioneer and Charity/Committee Leadership | Post Event Wrap Up | Soirée Logistic Work Group | Linda Blanton | 2017-03-17 | 2018-03-17
152 | Send Receipts if not provided at Auction | Post Event Wrap Up | Soirée Revenue Work Group | Anna Hall | 2017-03-17 | 2018-03-17
153 | 1/4 page Thank You Ad in FOT Sunday Life | Advertising | Soirée Engagement Work Group | Linda Blanton | 2017-03-19 | 2018-03-19 | Scheduled
154 | Update the auction contact list. | Greater Giving Go Time | Soirée Logistic Work Group | Linda Blanton | 2017-03-24 | 2018-03-24
155 | Arrange for shipment or delivery of items that were not picked up the night of the event. | Event Production | Soirée Logistic Work Group | Eileen Cedzo | 2017-03-24 | 2018-03-24
156 | Finalize the date for next year’s event. | Post Event Wrap Up | Soirée Logistic Work Group | Linda Blanton | 2017-03-24 | 2018-03-24
157 | Provide acknowledgements for volunteers (thank-you cards or a gathering). | Volunteer Management | Soirée Engagement Work Group | Daniele Malvesti | 2017-03-24 | 2018-03-24
158 | Reconcile budget, expenses and revenue to determine event results. | Post Event Wrap Up | Soirée Revenue Work Group | Linda Blanton | 2017-03-24 | 2018-03-24
159 | Send Photo and Press Release to Media | Post Event Wrap Up | Soirée Logistic Work Group | Linda Blanton | 2017-03-31 | 2018-03-31
160 | Begin Planning for your next Successful Benefit Auction! | Post Event Wrap Up | Soirée Revenue Work Group | Fiscal Dept | 2017-04-21 | 2018-04-21
161 | Send Thank you Notes | Post Event Wrap Up | Soirée Logistic Work Group | Linda Blanton | 2017-04-21 | 2018-04-21